## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | User Interface | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Frontend Developer | 2025-12-07 | Loan form submit button not sending data to backend API. | Sprint 1 | Backend Developer | User Interface | Fixed incorrect API route and enabled CORS. | 2025-12-08 | Closed | Form submission works properly.
2 | AI/ML Engineer | 2025-12-09 | AI model returning prediction but no explanation values (SHAP output empty). | Sprint 1 | ML Engineer | Logical | Corrected data preprocessing and SHAP initialization. | 2025-12-10 | Closed | Explanations generated correctly.
3 | Backend Developer | 2025-12-11 | Admin applicant list not loading due to pagination API response issue. | Sprint 2 | Frontend Developer | Logical | Updated pagination state handling and API mapping. | 2025-12-12 | Closed | Applicant list loads correctly.
4 | Full Stack Developer | 2025-12-13 | Customer dashboard showing old loan status after admin override. | Sprint 2 | Backend Developer | Maintainability | Corrected status update logic and added cache refresh. | 2025-12-14 | Closed | Dashboard reflects correct status.
5 | Chatbot Developer | 2025-12-15 | Chatbot not responding to eligibility-related questions. | Sprint 2 | NLP Engineer | Standards | Improved intent matching and added training phrases. | 2025-12-16 | Closed | Chatbot responds accurately.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others